## One month before
Done? | Activity | Your notes
Call in any favours and round up any helpers you might need
Make sure anyone roped in to help knows the date, time and addresses
Check the water parameters at the new place is similar to your current water supply
Depending on the results of checking the water - ensure you have the means to adjust the water parameters if needed
Find out where nearest fish shop is
Note opening times and phone number of nearest fish shop

## Two weeks before
Done? | Activity | Your notes
Remind any helpers of the date, time and addresses
Make sure you have enough fish bags, polystyrene fish boxes, insulated carriers, plastic boxes, bins, elastic bands, any required kit (see suggested kit list tab)
Collect enough blankets/old duvets etc. to pack around the aquarium

## One week before
Done? | Activity | Your notes
Make sure you know exactly where your aquarium will go in your new home, or in its temporary home.
Make sure you are familiar with the route from the vehicle to where the tank will go – check for any tight corners and make sure you can get the tank through any doorways, round any corners etc.
Make sure there are enough power sockets within reach; you may need to buy additional extension leads and RCDs.
Stock up on water conditioner and consumables such as fish food etc.
Prepare a moving day pack (see suggested kit list tab)
Prepare and print out at least two copies of your plan and checklist
Practice filling and tying any fish bags
Check the fish bags don't leak

## The day before
Done? | Activity | Your notes
Don’t feed your fish if you can avoid it
Run through the timings of everything
Make sure you have airstones, airlines and airpumps packed separately so that you can aerate the water in the fishes' containers on arrival if necessary
Switch the lights off to allow them to cool down

## On the day
a | Task | Duration in minutes - enter your timings here | Minutes from start - calculates for you | In hours - calculates for you
| Remove lights and coil up cables | 5 | 5 | 0.083333
| Turn off heater | 1 | 6 | 0.1
| Coil up cable for heater, bag plug | 2 | 8 | 0.13333
| Turn off airpumps, disconnect, pack | 5 | 13 | 0.21667
| Siphon out about 40% water, siphoning out substrate at the same time if required | 15 | 28 | 0.46667
| Tip water off subtrate and pack up substrate | 15 | 43 | 0.71667
| Remove plants | 10 | 53 | 0.88333
| Bag plants and pack | 10 | 63 | 1.05
| Remove bogwood/décor | 10 | 73 | 1.2167
| Bag bogwood/decor and pack | 5 | 78 | 1.3
| Fill bags/containers with water | 5 | 83 | 1.3833
| Catch fish and transfer to bags/containers | 20 | 103 | 1.7167
| Top up bags/containers with tank water if needed | 5 | 108 | 1.8
| Seal bags/containers | 5 | 113 | 1.8833
| Keep bags/containers warm with insulation | 2 | 115 | 1.9167
| Switch off filter | 1 | 116 | 1.9333
| Disconnect filter | 1 | 117 | 1.95
| Put filter canister in vehicle | 5 | 122 | 2.0333
| Remove filters hose, clean them, bag and pack them | 2 | 124 | 2.0667
| Siphon out as much water as possible (to jerry cans if taking with you) | 15 | 139 | 2.3167
| Remove any remaining substrate to bucket/bag | 10 | 149 | 2.4833
| Use sponge to remove rest of water from tank | 5 | 154 | 2.5667
| Clean tank | 2 | 156 | 2.6
| Dry tank | 5 | 161 | 2.6833
| Put tank in vehicle and pad with blankets | 5 | 166 | 2.7667
| Put stand in vehicle and pad with blankets | 5 | 171 | 2.85
| Put jerry cans of tank water in vehicle | 5 | 176 | 2.9333
| Pack plants, décor etc in vehicle | 3 | 179 | 2.9833
| Put fish in vehicle | 5 | 184 | 3.0667
| Pack any remaining boxes/bags of fish kit in vehicle | 5 | 189 | 3.15
| Pack all empty buckets etc. in vehicle | 3 | 192 | 3.2
| Drive to new house | 60 | 252 | 4.2
|  |  | 252 | 4.2
At the other end
| Unpack hardware - filter, power cables etc. | 10 | 10 | 0.16667
| Remove fish from vehicle and place somewhere warm if required | 5 | 15 | 0.25
| Unpack tank and check carefully for any signs of damage | 10 | 25 | 0.41667
| Set up the stand in the required place | 10 | 35 | 0.58333
| Set up power cables in the right places and plug everything in | 10 | 45 | 0.75
| Set up the aquarium on the stand | 5 | 50 | 0.83333
| Set up the filter pipework | 5 | 55 | 0.91667
| Set up airstones and heaters | 5 | 60 | 1
| Add substrate | 10 | 70 | 1.1667
| Add décor | 10 | 80 | 1.3333
| Add the old tank water you've brought | 10 | 90 | 1.5
| Add plants | 10 | 100 | 1.6667
| Top up to about 3/4 full with fresh water | 10 | 110 | 1.8333
| Check water parameters are correct | 3 | 113 | 1.8833
| Check temperature | 2 | 115 | 1.9167
| Add fish once temperature is correct |  | 115 | 1.9167
Collapse in a heap and have a cup of tea!

## Suggested kit list
bags for bogwood
bags for gravel
bags for plants
battery powered airpump
blankets/old duvets
bottle traps
buckets
dustbin and lid
dustpan
fish bags x 2 for each bagging required
heater and heater guard
hose and suitable connectors
inverter
large plastic boxes with lids
large plastic jug
large plastic trugs
nets
newspaper
old tea towels
old towels
pipe cleaning brush
ratchet straps
remote power switch for 3 pin socket and control
siphon
sponge
water pump
wide bore filter tubing